**XPRIZE HEALTHSPAN SEMI-FINALS TIMELINE EXAMPLE**

|  | **2025 Q1** | **2025 Q2** | **2025 Q3** | **2025 Q4** | **2026 Q1** | **2026 Q2** |
| --- | --- | --- | --- | --- | --- | --- |
| **MONTH** | **JAN** | **FEB** | **MAR** | **APR** | **MAY** | **JUN** | **JUL** | **AUG** | **SEP** | **OCT** | **NOV** | **DEC** | **JAN** | **FEB** | **MAR** | **APR** | **MAY** | **JUN** |
|  | **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | **11** | **12** | **13** | **14** | **15** | **16** | **17** | **18** |
| **XPRIZE MILESTONE 1 JUDGING** |
| XPRIZE Administrative Checks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Judges Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Semi-Finalist Notifications / Awards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **START-UP PHASE** |
| XPRIZE Team & Investor Summit |  |  |  | **TBD** | **TBD** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Clinical Protocol Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Regulatory Approvals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Staff Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **RECRUITMENT** |
| Team Participant Recruitment  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Baseline Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Intervention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Follow-Up Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **DATA ANALYSIS** |
| Team Analyze Clinical Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Analyze PK/PD or Biomarker Data (if needed) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Finalize Data and Analyses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **DATA SUBMISSION & FINALS APPLICATION** |
| Team Deadline: Submit Results Package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Deadline: Submit De-Identified Data Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Deadline: Submit Finals Testing Application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **XPRIZE MILESTONE 2 JUDGING** |
| XPRIZE Administrative Checks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE DCC Verification and Collate Results |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Judges Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Finalist Notifications and Awards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

**Judging Questions on Timeline:**

* Is the study timeline adequately described, taking into account start-up activities, recruitment, and planned assessment for Semi-Finals?
* Is there a proposed plan for how the Semi-Finals studies will expedite transition to Finalists’ 1-year clinical trials?
* Are regulatory materials prepared or approvals in process, and is this included in the proposed 1-year timeline?
* Are strategies in place should regulatory timelines be missed or delayed?
* Does the project incorporate efficiencies and utilize existing resources to increase the rate of participant enrollment, study start-up, and data collection, as appropriate?
* Are potential challenges that may impact timeline and corresponding solutions discussed in Qualifying Submission?