## Slide 1
2024 Work Plan

## Slide 2
YCC Roles & Responsibilities
Per County Ordinance, the YCC duties are:
Providing recommendations to the Board of Supervisors (Board), Chief Sustainability Office (CSO), and County departments on new or existing County initiatives related to climate mitigation and adaptation.
Providing input on the OurCounty Annual Report, near term priorities, and funding strategies.
Providing recommendations on existing or proposed climate-related legislation, policies, or initiatives, especially regarding its impact on youth.
Publishing Annual Report on YCC activities and achievements.
Working with other County Commissions, boards, and committees.
Conducting outreach and communications to youth under 18.

## Slide 3
2024 Proposed Workstreams
To advance the goals of the YCC, the following four workstreams are proposed:
Workstream I: Stay apprised of State, Federal, and County legislation and provide feedback where relevant.
Workstream II: Advise on the development of the OurCounty Annual Report and the launch of the OurCounty refresh.
Workstream III: Consistent engagement with youth and development of District-specific actions based on priorities.
Workstream IV: Communicate and work with the Board, County departments, and the public about YCC priorities and progress.

## Slide 4
Workstream I
Workstream I: Stay apprised of State, Federal, and County legislation and provide feedback where relevant. | 
Purpose | 
Recommend County positions on legislation and development of Board motions. | 
Actions | Lead
Establish subcommittee/ad hoc to quickly respond to requests, track legislative developments, and recommend actions to YCC. | YCC
Provide regular updates on what is on the State, Federal, and County legislative calendar. | CSO
Seek YCC input as climate-related legislation and motions develop. | CSO
Notes: Note the suggestion to have an Ad Hoc

## Slide 5
Workstream II
Workstream II: Advise on the development of the OurCounty Annual Report (release Fall 2024) and the launch of the OurCounty refresh (begins Summer 2024). | 
Purpose | 
Provide youth perspective on current and future climate action planning and priorities. | 
Actions | Lead
Provide input to the CSO on the OurCounty Annual report and refresh. | YCC
Advise and support community engagement on Annual Report and refresh to ensure youth voices are heard and incorporated. | YCC
Stay apprised of and provide input on other OurCounty-related initiatives, including the Urban Forest Management Plan and Heat Action Plan. | YCC
Provide regular updates to YCC on OurCounty progress and other important climate-related issues. | CSO
Notes: Flag the UFMP workshops through mid Feb and draft report released in mid-March

## Slide 6
Workstream III
Workstream III: Consistent engagement with youth and development of District-specific actions based on priorities. | 
Purpose | 
Build youth capacity by educating them on the YCC and County climate work while also continuously seeking out youth input on priorities and concerns. | 
Actions | Lead
Host 3 meetings in each District to seek youth input on priorities and share YCC work. | YCC
Present or table at 5 events per Commissioner with a particular focus on youth attended events. | YCC
Establish and maintain District-specific Instagram promoting YCC and other climate news. | YCC
Host at least 3 youth-focused events on climate-related topics and youth capacity building, seeking collaboration opportunities with other youth-focused Commissions/Councils. | YCC

## Slide 7
Workstream III (cont’d)
Workstream III: Consistent engagement with youth and development of District-specific actions based on priorities. | 
Purpose | 
Build youth capacity by educating them on the YCC and County climate work while also continuously seeking out youth input on priorities and concerns. | 
Actions | Lead
Support outreach activities by connecting Commissioners to opportunities, helping to secure venues, providing support materials, offering technical assistance, and more. | CSO
Maintain YCC Instagram with at least 5 posts/year and publication of quarterly YCC newsletter. | CSO
Provide YCC template presentation, speaker training, and technical assistance as needed. | CSO
Notes: Reminder that we’re offering another social event in late February where we’ll also offer speaker training

## Slide 8
Workstream IV
Workstream IV: Communicate and work with Board, County departments, and public on YCC priorities and progress | 
Purpose | 
Take action on priorities and keep Board and departments apprised of youth perspective so they can be inputted into County decision-making and ensure transparency and accountability with the public. | 
Actions | Lead
Publish results of Youth Climate Priorities Survey with recommendations and next steps, and share with Board and other relevant departments. | YCC/CSO
Identify and take action on top priorities from Youth Survey. | YCC
Publish public Annual Report (Sept 2024) and submit to Board. | YCC/CSO
Invite key departments to present on important developing climate-related work for YCC feedback. | CSO