## Instruction
Strategy | Action
Governance | Decision |  | Completed | Goal | Action
Process | Information | Status | On track | Issue | Decision
People |  |  | Potential risk |  | Escalation
Culture |  |  | Risk |  | Information
Performance |  |  | Issue
What is the purpose of the tool?
This Action list is used to manage the multiple actions required, to log key items for the upcoming meeting and the decisions made. All in one file. The drop down menus and the filter function will easily help you track and manage your project progress.
When should the Action list be developed?
It should be developed during Initiation Phase and then updated regularly throughout the life of the project.
Who creates the Action list?
The Action list can be created and owned by Program or Project Manager and created in combination with team members. It is a file that need to be update by all action owners regularly.
Step 1: Fil in the date and item number
Complete the first fields of the template. This helps you to filter and manage progress
Step 2: Fill in Type, Subject or theme and Goal or issue.
Select in the dropdown menu:
What is the item type: Action, Decision or Information. This tells you what is needed.
What is the subject of this item: Strategy, Governance, Process, People, Culture or Performance.
Is it a goal or a issue.
Step 4: Describe the Action, Owner and Due date
Describe the action needed, short and succinctly, so that all team members understand the item and what is needed.
Select a owner of the item, he or she will update the status and add remarks recurrently. Also mention is someone else is involved with this item to maintain a good overview of team load.
In the column Due date the owner will mention estimated date of completion for the item.
Step 5: Status and Date closed
Every meeting or update, the owner of the item will update the status, and add remarks so that progress of each item can be tracked. Once an item is finished, the Date closed will be added for completion of this file
Extra: Meeting guidance - key items and Decisions overview
These two extra sheets helps you to stay organized as all link to the items in the action list.

## Actions
Project: | <...>
Last Updated: | <…>
Plan |  |  |  |  | Do |  |  |  | Check |  | Act (or Remarks)
Date | Item # | Type | Subject/ Theme | Goal/ Issue | Action | Owner | Who Else | Due date | Status | Date Closed | Remarks
Notes

## Decisions overview
Decision overview
Item # | Subject / theme | Status/ Proposal | Date Proposed | Decision

## Meeting guidance - Key Items
Key Items for this Meeting:
Action, Decision, Escalation or Information
| Item # | Subject/ theme | Status/ Proposal | Type | Source
1
2
3
4
5
6
7
8
9
10
11
12